## Burndown Chart
Group 4 Burn Down Chart
Sprint | Total Stories | User Stories | [5 empty] | Story Points | Story Points Completed | Ideal Burn Down | Story Points Left | Ideal Burn Down
Inception | 4 | As a | student | I want to | have a brief overview of the problem, a preliminary timeline, and an initial analysis of the data | so that | we can confirm that our plan aligns with the goals of the client in a reasonable timeline | 20 | 20 | 20 | 125 | 125
| 2 | As a | student | I want to | have a preliminary story point/task list | so that | the team can refer to what they should be working on based on priority | 10 | 10 | 10 | 115 | 115
| 3 | As a | student | I want to | have a detailed group plan and centralized software | so that | the goals of the project are being met by all team members | 10 | 10 | 10 | 105 | 105
1 | 2 | As a | student | I want to | work with data that is close to real life accuracy | so that | it is easiest to analyze and pull pertinant data from | 20 | 10 | 20 | 95 | 85
| 3 | As a | Primoris executive | I want to | have a document detailing the adjustments to the data to make it easier to work with | so that | that we can be informed where data issues lie and also have a catelog of what has been cleaned and how | 10 |  | 10 | #N/A | 75
2 | 1 | As a | student | I want to | monitor the rate that we are completing tasks | so that | we can be sure to stay on time and add/remove tasks that are futher down in the backlog list | 5 |  | 5 | #N/A | 70
| 1 | As a | student | I want to | analyze the process of how we are accomplishing tasks as a team | so that | adjusmtent can be made to become an even more successful group | 10 |  | 10 | #N/A | 60
3 | 1 | As a | student | I want to | have a preliminary story point/task list | so that | the client can see the work completed, and see if there are things that we had planned and did not accomplish are necessary would like to extend us to complete them | 10 |  | 10 | #N/A | 50
| 4 | As a | Primoris executive | I want to | have a final model performance report | so that | we can see what insights from the analyzation are | 20 |  | 20 | #N/A | 30
Transition | 1 | As a | Primoris executive | I want to | have a presentation to overview what we are delivering | so that | how we can implement our strategy, and the benefits of it | 10 |  | 10 | #N/A | 20
| 5 | As a | Primoris executive | I want to | have a document detailing the in depth description of the models used to create insights from the data | so that | we can understand from a technical perspective, what insights were gathered and how | 20 |  | 20 | #N/A | 0
Totals | 27 | [6 empty] | 145 | 50 | 145
Rafael Cintron: rafael.cintron@colorado.edu, Supria Deka: supria.deka@colorado.edu, Pranathi Manthri: pranathi.manthri@colorado.edu, Murali Prateek Manthri: murali.manthri@colorado.edu, Jinal Mehta: jinal@mehta@colorado.edu