## User Stories
Story | Story Point | Sprint | Status | As a | User | I want to | Feature/Goal | so that | Reason/Benefit | Definition of Done
1 | 20 | Inception | Done | As a | student | I want to | have a brief overview of the problem, a preliminary timeline, and an initial analysis of the data | so that | we can confirm that our plan aligns with the goals of the client in a reasonable timeline | Submit an agile and data analysis report titled S25_Team4_Agile_Data_Report
2 | 10 | Inception | Done | As a | student | I want to | have a preliminary story point/task list | so that | the team can refer to what they should be working on based on priority | Submit a preliminary project backlog excel spreadsheet titled S25_Team4_Project_Backlog
3 | 10 | Inception | Done | As a | student | I want to | have a detailed group plan and centralized software | so that | the goals of the project are being met by all team members | Have a software set up for project 1 with sprints and tasks that everyone has acccess to
4 | 20 | Sprint 1 | Done | As a | student | I want to | work with data that is close to real life accuracy | so that | it is easiest to analyze and pull pertinant data from | Have data cleansed from most missing information, duplicate rows, inconsistencies, and anomalies
5 | 10 | Sprint 1 | Done | As a | Primoris executive | I want to | have a document detailing the adjustments to the data to make it easier to work with | so that | that we can be informed where data issues lie and also have a catelog of what has been cleaned and how | Submit a report on the cleanup process of the data titled S25_Team4_Data_Cleanup_Report
6 | 5 | Sprint 2 | Done | As a | student | I want to | monitor the rate that we are completing tasks | so that | we can be sure to stay on time and add/remove tasks that are futher down in the backlog list | Create a Burndown Chart detailing Story Points Remaining on the Y-axis and Sprints on the X-axis. There should be two lines, one is the projected or goal line, and the other is actual which will be updated daily. Submission should be called S25_Team4_Burndown_Chart
7 | 10 | Sprint 2 | Done | As a | student | I want to | analyze the process of how we are accomplishing tasks as a team | so that | adjusmtent can be made to become an even more successful group | Submit a Project 2 Sprint Retrospective Project Report titled S25_Team4_Sprint_Retrospective
8 | 10 | Sprint 3 | Done | As a | student | I want to | have a preliminary story point/task list | so that | the client can see the work completed, and see if there are things that we had planned and did not accomplish are necessary would like to extend us to complete them | Submit the final project backlog excel spreadsheet titled S25_Team4_Project_Backlog
9 | 20 | Sprint 3 | In Progress | As a | Primoris executive | I want to | have a final model performance report | so that | we can see what insights from the analyzation are | Submit a model performance report titled S25_Team4_Model_Performance_Report
10 | 10 | Transition | To do | As a | Primoris executive | I want to | have a presentation to overview what we are delivering | so that | how we can implement our strategy, and the benefits of it | Submit the slides created for the client titled S25_Team4_Slides
11 | 20 | Transition | To do | As a | Primoris executive | I want to | have a document detailing the in depth description of the models used to create insights from the data | so that | we can understand from a technical perspective, what insights were gathered and how | Submit a final report of models and analysis titled S25_Team4_Final_Report
*Stories that are bolded mean they are a deliverable